## Sheet1
# | Action Items | Who | Status | Comments
Meeting 9 Oct 2018
15 | Jurisdictional demonstrations to be included in future MDWG meeting agendas | MDWG Secretariat | Completed
16 | Shared Metadata Infrastructure | Andrew Whiting | Completed | Survey of the current metadata systems was conducted. Results are getting summarised now.
# Define what this shared metadata infrastructure capability is in further detail
| # Establish a strong relationship with data.gov.au and explore their scope for hosting metadata, whilst ensuring custodians business requirements can be stained |  | Not done | Email was sent to DTA data.gov.au activity manager.
17 | MDWG Secretariat to keep in touch with Nicholas Brown, monitoring GDA2020 developments and requirements of the group | MDWG Secretariat | Completed | Continue engagement with Nicholas Bown
18 | Prepare a web presence articulating the roadmap tranches | RMSG and Secretariat | Completed
19 | Circulate to the MDWG the deliverables roadmap spreadsheet for further feedback | MDWG Secretariat | Completed
20 | Explore a Trello board or other, to monitor the activities associated with the roadmap | MDWG Secretariat | Completed | Website will be used as the monitoring tool. discussion forum page
21 | Have the roadmap status as a standing item on the groups agenda for status reporting | MDWG Secretariat | Completed
22 | Produce a narrative clearly articulating the proposed profile framework – explicitly articulating what it is and why it is different to past ANZLIC profile activities | Profile Sub Group | Completed | Graham's narrative, send as a package
23 | Clearly articulate and describe what each of the elements is within the recommended profile comparison | Profile Sub Group | Completed | Byron's work, send as a package
24 | Continue to make additions to the mapping spreadsheet – and document each of the jurisdiction mappings | Profile Sub Group , George Mansour | Completed | Contact people about their profiles
| # George Mansour to share with the PSG DELWP’s chosen elements, for inclusion in the mapping document |  | Completed
25 | Circulate the profile comparison to the MDWG for any further comment and feedback | MDWG Secretariat | Completed | send as a package
26 | Develop and undertake a survey to identify what each MDWG’s metadata capabilities are identifying what systems or applications currently develop, manage or disseminate metadata | Profile Sub Group | Completed | Check with Nick, Andrew to send a survey to MDWG
27 | MDWG members interested in the technical working group to contact Irina.Bastrakova@ga.gov.au | All | Completed
28 | Kate Roberts (BOM), Ian Beitzel (Qld), Aaron Sedgmen (GA) and Adam Rice (DTA) wished to be included into this working group |  | Completed
29 | PSMA to be invited to the MDWG, with relation to the API associated activities | Irina Bastrakova | Completed
30 | Approach the Imagery Working Group, with a recommendation that the MDWG believe the 19115-2 standards need to be considered and worked upon. | Irina Bastrakova | On Hold | Delay with the standards release: it was released in January 2019, The PCTI is under its structure review, it may be divided into two parts.
31 | Defence, ACT, VIC, QLD and GA to define common requirements related to 19115-2, and 19165 standards. Consider how these requirements would be addressed within the associated standards | Irina Bastrakova | On Hold | Clarify at the next meeting
32 | Defence, ACT, VIC, QLD and GA to discuss further and report back to MDWG and the profile sub-group. | Irina Bastrakova | On Hold | Clarify at the next meeting
33 | Explore Trello and GovTeams for the hosting and management of the roadmap activities | MDWG Secretariat | Completed | GovTeams do not cover states, Confluence to be used instead
Meeting 3, February 2019
34 | Feedback on Terms of Reference to MDWG | Evert Bleys | Completed
35 | Publish de-identified baseline survey results on ICSM website in pdf format | MDWG Secretariat | Completed
36 | Short report on the survey for circulation to MDWG (and ICSM). | Andrew Whiting | Completed
37 | Lessons learnt register to be created and circulated | Dave Connell | Completed
38 | Provide missing elements to spreadsheet | Evert Bleys | Completed
39 | Nick Car to turn ISO code lists into a Linked Data Vocabularies, where required | Simon Cox | Completed | Task was assigned to Nick Car. Simon Cox completed the task:https://vocabs.ands.org.au/search/#!/?pp=15&q=TC211&p=2
40 | Loomio - Byron to setup Loomio as collaboration tool | Byron Cochrane | Completed
41 | Finalise the High level document on the Australian Metadata Profile | Byron Cochrane | Completed
42 | Present the Australia Metadata Profile at the ICSM Meeting | Graham Logan | Completed | The work of the MDWG was also presented at the Locate19, EGU and E2SIP
43 | Publish the Australia Metadata Profile at the ICSM Metadata Webside | MDWG Secretariat | Completed
44 | Progress work on the best practices for the Australia Metadata Profile document | Technical MDWG | Completed
Meeting 4, June 2019
45 | MDWG members to review the TORs and provide feedback to Andrew Whiting by 21 June | MDWG | Completed
46 | Nick Brown to supply link for ITRF transformations, on ITRF website | Nick Brown | Completed
47 | Requirement to prepare guidelines of how store datum in metadata level – need to dive into feature level, not just product level. | Technical MDWG | Completed | Draft distributed on 19/09/2019
48 | MDWG members to contribute datum use case stories to PCG | MDWG | Not available
50 | Need to discuss further associated resource | Technical MDWG | Completed
51 | EMSINA to come and talk about machinery aspect | Andrew Whiting | Completed | The ICSM MDWG achivements were presented at EMSINA, Dec 2019. Waiting for their response
52 | Investigate how to represent data created on fly and report back to MDWG | Technical MDWG | On Hold
53 | Examples of abstract and purpose statements to be provided to Byron | MDWG | Not available
54 | People who wants to provide input to Blueprint discussions request access to Loomio from Byron. | MDWG | Completed
55 | All – Example of use cases for high-precision positioning requirements | MDWG | Not available
56 | ICSM MDWG Promotion: Submit an abstract to eReserach 2019 | Irina Bastrakova | Completed
57 | Additional ICSM MDWG members –send email to Irina | MDWG | Completed
58 | Finalise the element description and to prepare a draft of the Blueprint document by the next meeting | Technical MDWG | Completed
59 | Promotion:Wellington, Nov, Plenary at the OGC meeting; | All | Completed
60 | Recommendation for metadata for services | Melanie Barlow/ Technical MDWG | Completed
61 | Review of the storyboard for the metadata video | All | Completed | Feedback by 1 November 2019
Meeting 5, Oct 2019
5.1 | Members to provide input into preliminary storyboard notes | All | Completed | Video published
5.2 | Irina to send transcript, communication video and questions | All | Completed | Video published
5.3 | Shanti to discuss input into international standards with colleague (experts in simulation world) | Shanti | In progress | Waiting for response
5.4 | Provide links to published vicabularies on MDWG website | Irina/Jenny | In progress
5.5 | Organise review roadmap at next meeting | Irina | Completed | Meeting 6 agenda item
5.6 | Request for funding - ICSM meeting | All | Completed | ICSM requested to table the proposal
5.7 | Provide examples of service type constracts (e.g. elements of getCap) | Melanie | Completed | Some examples were provided
5.8 | Contact Melanie to join the Geospatial Capabilities Cop | All | Completed
5.9 | Present about MDWG at Geospatial Capabilities CoP | Irina | Completed
5.1 | Provide recommendation to document protocols and service type | Technical MDWG | In progress | Information is reviewed
5.11 | Best practice for metadata for services document | Melanie / Aaron | In progress
5.12 | Share vocabulary lists to publish as public access via RDA portal | All | Continuous Item | Published the ISO 109115-1 vocabularies
5.13 | Review of ANZLIC vocabularies | Technical MDWG | Not started | To be confirmed at the Meeting 6
5.14 | Developing communication materials | TBC | Not started | To be addressed through the Roadmap V2
5.15 | Organise surveys for metadata for imagery and digital adta preservations | Irina | Completed | the surveys were completed
5.16 | Develop market survey to gauge input to gather use cases |  | Not started | From responses to MDWG questions, e.g. imagery and Lidar Working Group,
5.17 | NAA role in providing guidance around ISO 19165 needs to be clarified |  | Not started
5.18 | DoEE to share recordkeeping reference with group |  | Completed
5.19 | Evert to send link to xsd for Preservation Standard available from GitHub | Evert | Completed
5.2 | Publish Best Practie Document | Irina/Jenny | Completed
5.21 | Publish Metadata for Services (Table) | Irina/Jenny | Completed
5.22 | Paper Joel presented to OGC in Banff to be distributed | Irina | Completed | Report from the trip was provided
Meeting 6, March 2020
6.1 | Contact OGC (Chris Little?) re publication of a vocabulary of authoritative definitions of different temporal reference systems | Irina Bastrakova & Aaron Sedgeman |  | 2020-04-15
6.2 | Imagery/Acquisition Survey:
6.2.1 | Build collaboration with ICSM imagery/elevation working group and seek provision of their requirements | Irina Bastrakova |  | TBC
6.2.2 | Analyse feedback received on requirements and develop crosswalks to ISO 19115-1 and 19115-2 (and other standards as required) | Technical MDWG |  | TBC - after 6.2.1
6.2.3 | Inform ISO TC211 of MDWG work and provide feedback to them as required | Irina Bastrakova |  | TBC - after 6.2.3
6.2.4 | Present findings and propose new profile at next ICSM MDWG meeting | Technical MDWG |  | 2020-07-31
6.3 | Metadata for Digital Data Preservation Survey:
6.3.1 | Contact NAA to raise awareness on MDWG requirements | Irina Bastrakova |  | 2020-04-30
6.3.2 | Identify relevant jurisdicitonal agencies, policies, regulations and standards | MDWG, Irina to send email |  | 2020-05-30
6.3.3 | Analyse policies/standards | Technical MDWG |  | 2020-06-30
6.3.4 | Present findings and propose new profile at next ICSM MDWG meeting | Irina Bastrakova |  | 2020-07-31
6.4 | Examples of "profiles" that maybe don't need to be a standard, but may be better as best practice documents (eg. satellite imagery); Share comparison between US motion imagery standards and ISO 19115; Seek Secretary of EMSINA's perspective on their use of standards | Kate Roberts; Shanti Rowlinson; Irina Bastrakova |  | 2020-04-15
6.5 | Send links for any existing best practice guides or profiles to Irina (e.g. sattelite imagery, US defence imagery standards | Kate Roberts; Shanti Rowlinson; MDWG |  | 2020-04-15
6.6 | Organise Google doc to allow capture of Coordinate Epoch issues; review and record any solutions in same document | Byron Cochrane |  | 2020-04-03
6.7 | Dedicate next Technical MDWG teleconference (3 April) to Coordinate Epoch issue | Irina Bastrakova | Completed | 2020-04-03
6.8 | Invite Zarina to attend next Technical MDWG meeting (3 April) | Shanti Rowlinson | Completed | 2020-04-03
6.9 | Provide feedback on MDWG website to aid review - looking to add more structure, and is there anything missing? | MDWG |  | 2020-04-30
6.10 | "What are current metadata challenges for Australian Government and how can they be addressed?" Provide feedback to NAA (information.management@NAA.gov.au), or send feedback to Irina to collate and submit on behalf of group | MDWG |  | 2020-04-30
6.11 | Advise Irina Bastrakova if interested in attending a specific workshop around vocabularies at a future MDWG meeting. If so, potential to have Nick Car involved? | MDWG |  | TBC- this question should be part of the email with minutes
6.12 | For discussion: Jenny Mahuika seeking guidance on online resources and protocol - how codelists should relate | Technical MDWG |  | 2020-04-03
6.13 | Provide feedback on issues/benefits experienced with ZOOM meeting format to Irina | MDWG | Completed | 2020-04-03
6.14 | Review actions from MDWG Roadmap v1 and clarify any new actions going forwards:
6.14.1 | Review 19115-1 profile as required | Technical MDWG |  | TBC
6.14.2 | Identify gaps and crosswalks between 19115-3 and DCAT standards with aim to generate relevant geoJSON | TBC, potentially Aaron and Byron |  | TBC
6.14.3 | Identify differences between schema.org and 19115-3 and see if there is a validation tool and/or creation tool for JSON | TBC |  | TBC
6.14.4 | Review poster of core elements from new profile, seeking input from EMSINA Secretary | Irina Bastrakova |  | 2020-04-30
6.14.5 | Add poster to Resource list | Irina Bastrakova |  | 2020-04-30
6.14.6 | Collect and publish statements about implementation/benefits from use cases that have progressed | MDWG |  | 2020-05-30
6.14.7 | Review Register of Tools and Resources for new profile implementation, and provide feedback including advice re any items which should be added | Technical MDWG | Completed | 2020-04-02
6.14.8 | Review Register of metadata management systems, and provide feedback including advice re any items which should be added | Technical MDWG | Completed | 2020-04-02
6.14.9 | Provide testamonials articulating how metadata is used and why it is important within your business, for publication on MDWG website | MDWG |  | 2020-05-30
6.14.10 | Document governance and procedure for updating Best Practice Guide | Byron Cochrane |  | 2020-04-30
6.14.11 | Provide access to any new versions of the Best Practice Guide on the MDWG website | GA |  | As required
6.14.12 | Define communication channels to relevant stakeholders | MDWG |  | 2020-07-31
6.14.13 | Discuss requirements with EMSINA and, dependent on staff availability, seek funding to create procedures for transition to 19115-3 based on one of their themes | Irina Bastrakova |  | TBC
6.14.14 | Become more active in MDWG communications and promotions activities; take a more influential role | MDWG |  | TBC
6.14.15 | Develop workflow or diagram with defined starting and end points so users can identify where they are currently and where they want to be, which will give them the steps required to get to implementation | Melanie Barlow, Technical MDWG |  | 2020-05-30
6.14.16 | Create governance process for vocabularies | Technical MDWG |  | 2020-05-30
6.14.17 | Ongoing action now revised for incorporation into the new Roadmap: "Monitor and participate in standards development within ISO and OGC" | Technical MDWG |  | 2020-05-15
6.14.18 | Identify any new applicable standards and provide crosswalks (from Tranche 1 discussion) | Technical MDWG |  | as required
6.14.19 | Develop a communication strategy defining our stakeholders and available communication channels | TBC |  | TBC
6.14.20 | Identify and assess suitability of potential tools/workflows, eg. geoNetwork or MAGDA | Technical MDWG |  | TBC
6.14.21 | Extend table list of action items identified at meetings to include items identified between meetings | Irina Bastrakova | Completed | 2020-04-15
6.14.22 | Publish table list of action items on MDWG website for easy access | GA | Completed | 2020-05-10
6.14.23 | Complete templates created for 24 March Workshop Activity 1 and Activity 2 (to be distributed by Irina Bastrakova) | Irina Bastrakova; MDWG | Completed | 2020-04-03